## Sheet1
Months | Days to Final Occupency |  | Task
11 | 342 | 1998-03-09 | Called city on timing for print approval - stated 2 weeks.
| 331 | 1998-03-20 | Called Civil Engineering Firm - request quote for Plot Plan, Preliminay and Final Grade Certificate
| 328 | 1998-03-23 | Made 10 copies of house prints; Delivered one set of house prints to Civil Engineering Firm - for plot plan
| 325 | 1998-03-26 | Called Heating Engineer - provided floor plan prints
| 324 | 1998-03-27 | Civil Engineer called and based on dimensions of lot, I need to shrink the house 2 ft.
| 319 | 1998-04-01 | Looked at prints and determine where 2 ft will be removed - made changes and told Civil Engineer
| 318 | 1998-04-02 | Picked up prints at Civil Engineer and submitted plot plan , heating plan and house prints to city. Paid city fees.
| 307 | 1998-04-13 | Requested quotes from underground escavator, basement wall company, trenching company and rough lumber yard.
| 304 | 1998-04-16 | City completed plan review. Provided list of errors requiring corrections.
10 | 303 | 1998-04-17 | Went to lumber yard with prints for "Take-off". Ie Quote on lumber needed.
| 299 | 1998-04-21 | Quotes arrived from Trenching, escavator, basement wall company
| 295 | 1998-04-25 | Called Insurance company and bought Builders Risk Insurance
| 293 | 1998-04-27 | Gave set of prints to lumber yard; Plans approved by City
| 290 | 1998-04-30 | Called Civil Engineering Firm - requested basement stake-out and utility stake-out; hired escavator
| 289 | 1998-05-01 | Stake-out couldn't happen due to rain
| 287 | 1998-05-03 | Basement and utilities staked-out
| 278 | 1998-05-12 | Basement dug
| 277 | 1998-05-13 | Called and scheduled basement wall company. Plan to put footings in early next week.
| 276 | 1998-05-14 | Got quotes in from Lumber yard. Trenching company needs plot plan and Building Permit #.
| 274 | 1998-05-16 | Made a sign with the Lot Number and put in on the lot. Escavator did Final Grade.
9 | 270 | 1998-05-20 | Basement wall company installed footings.
| 268 | 1998-05-22 | Basement wall forms delivered & footing forms were removed.
| 266 | 1998-05-24 | Basement walls forms installed - ready for cement pour. Called Escavator - requested he add Sump Line.
| 264 | 1998-05-26 | Basement wall poured. Started to look for Rough Carpenters.
| 262 | 1998-05-28 | Basement wall forms removed - footprint looks small for it's accurate. Checked on Escavator for back-fill - ready anytime.
| 259 | 1998-05-31 | Basement walls tared and drain tiles installed.
| 258 | 1998-06-01 | Back-fill done. Called Civil Engineering to do a Rough Grade Certificate
| 256 | 1998-06-03 | Called Trenching company - scheduled. Called Lumber yard - had lumber scheduled
| 253 | 1998-06-06 | Went to lot and measured the beam slots across the basement (to order the metal beams)
| 252 | 1998-06-07 | Spoke to Rough Carpenters - need lumber and metal beams delivered on Wednesday and Truss on Friday. Called Lumber yard.
| 251 | 1998-06-08 | Trenching complete. They called inspections. Rough Grade Certificate sent to City.
| 249 | 1998-06-10 | Lumber and beams on lot
| 248 | 1998-06-11 | Sent out prints to Heating, Plumbing and Electrician
| 247 | 1998-06-12 | Rough Carpenters started roughing the house
| 245 | 1998-06-14 | Got quotes in from Heating, Plumber and Electrician. Signed contracts.
| 242 | 1998-06-17 | Second floor of house is up. Windows and Doors schedueled for tomorrow
| 241 | 1998-06-18 | Windows and doors arrived at lot. Placed in garage. Called company for Garage doors.
| 241 | 1998-06-18 | Called roofers for quotes.
8 | 240 | 1998-06-19 | Rough Carpenters installed windows and exterior doors; Looked at Brick types
| 239 | 1998-06-20 | Paid Rough Carpenters got waiver. Started to clean up lot.
| 235 | 1998-06-24 | Heating work started today. Roofers to start in a couple of days.
| 233 | 1998-06-26 | Plumbers need peagravel - called yard had delivered, Plumbers started in basement. Rough Heating finished
| 232 | 1998-06-27 | Sent quotes out for Alarm and Central Vacuum.
| 230 | 1998-06-29 | Called insulation companies - asked for quotes. Called Lumber yard to pick up remaining lumber for credit.
| 229 | 1998-06-30 | Electrican called will start in a couple of days. Plumbres should be done by then.
| 228 | 1998-07-01 | Roofers should start today
| 227 | 1998-07-02 | Rough Plumbing compete. Roofers to start in a few days
| 225 | 1998-07-04 | Roofers started. Confirmed Brick Layers will start on Monday
| 220 | 1998-07-09 | Plumbing inspection failed - list on Window to correct.
| 219 | 1998-07-10 | Cement contractor picked and scheduled.
| 218 | 1998-07-11 | Went to Brick Yard to pick out brick. Had Brick delivered. Shingles are done.
| 216 | 1998-07-13 | Brick Layers started today. Electrician Done.
| 215 | 1998-07-14 | Plumbing re-inspection planned for tomorrow. Electrian Inspection Failed for two items.
| 214 | 1998-07-15 | Brick layers still working, Picked-up iron for over windows and doors.
| 212 | 1998-07-17 | Plumber did not return to do repairs, Electrian did return to do repairs.
| 211 | 1998-07-18 | Brick layers finished.
7 | 209 | 1998-07-20 | Sump line installed by Escavator
| 207 | 1998-07-22 | Plumbers completed repairs and called for inspection
| 206 | 1998-07-23 | Plumbing inspection complete. Called Cement Contractor to pour basement and garage.
| 205 | 1998-07-24 | Drywall company came in to measure house for quotes.
| 204 | 1998-07-25 | Window broken due to vandelism - got Police Report
| 203 | 1998-07-26 | Sent claim to insurance company. Called Alarm Company for install.
| 201 | 1998-07-28 | Cement prep-ed and ready for pour.
| 200 | 1998-07-29 | Started to wire the house for telephone, cable, and Cat5
| 199 | 1998-07-30 | Requested quotes from cabinet companies, started to look for tile
| 197 | 1998-08-01 | Cement inspection passed - pour scheduled
| 195 | 1998-08-03 | Called Rough Inspection - failed list of 9 items to fix. Called rough carpenter.
| 193 | 1998-08-05 | Alarm company started to install alarm and central vacuum system
| 192 | 1998-08-06 | Basement and Garage Cement planned for tomorrow
| 191 | 1998-08-07 | No cement due to rain. Broken window replaced.
| 187 | 1998-08-11 | Cleaned inside of house. Cement poured.
| 186 | 1998-08-12 | Working on Rough Inspection Fixes
6 | 177 | 1998-08-21 | Called City for water tap - 10-15 days to install
| 174 | 1998-08-24 | Hired cleaners to clean up site.
| 171 | 1998-08-27 | Met with Engineer to determine fixes for Rough Carpentry
| 168 | 1998-08-30 | Rough Carpenters started fixing the issues.
| 167 | 1998-08-31 | Called and scheduled brick cleaners and caulking
| 166 | 1998-09-01 | Called for Rough re-inspection
| 164 | 1998-09-03 | City inspected the house - Failed again
| 162 | 1998-09-05 | Made more repairs (seem to find new things wrong)
| 159 | 1998-09-08 | Failed Rough Inspection again - at least less items
| 158 | 1998-09-09 | Made more repairs to new items..
| 157 | 1998-09-10 | House passed inspection!
| 156 | 1998-09-11 | Called to get house insulated
| 155 | 1998-09-12 | House insulated. Called Drywall Company for timing.
| 154 | 1998-09-13 | Called Basement Wall Company - need basement walls painted (part of quote)
5 | 152 | 1998-09-15 | Insulation inspection passed. Drywall arrived
| 148 | 1998-09-19 | Cleaned up house again.
| 146 | 1998-09-21 | Drywall company plans to start in next couple of days.
| 145 | 1998-09-22 | Basement wall company will paint the inside walls ealy next week.
| 144 | 1998-09-23 | Called Heating Contractor to get furnance installed - Cold Weather is coming.
| 142 | 1998-09-25 | Called Vinyl companies for outside trim - need to close up the house due to the colder weather coming
| 141 | 1998-09-26 | Drywall started. Quotes for Outside trim and outside cement
| 140 | 1998-09-27 | Ordered garage door. Basement heating ducts are in.
| 138 | 1998-09-29 | All Drywall installed. Mudding to start. Vinyl Company quote accepted.
| 137 | 1998-09-30 | Requesting quotes for Tile work
| 135 | 1998-10-02 | Called siding, stone and cleaner for prices
| 131 | 1998-10-06 | Siding and stone installers will review job today for pricing
| 131 | 1998-10-06 | Tile installer called and provided pricing
| 130 | 1998-10-07 | Cleaned house and through all the trash in garage, called cleaners to pick up trash
| 128 | 1998-10-09 | Installed garage doors, insulation started
| 127 | 1998-10-10 | Painters provided prices, Called for drapes - got prices
| 125 | 1998-10-12 | House was mudded - need to keep house warm for it to dry - used heaters
| 123 | 1998-10-14 | Stone installers started
4 | 120 | 1998-10-17 | Cleaned up drywall and debres
| 115 | 1998-10-22 | Plumbers will install gas line, tile started
| 113 | 1998-10-24 | Cabenets arrived
| 112 | 1998-10-25 | Cabenets installed. Painters primed house
| 111 | 1998-10-26 | Called heating contractor to install registers
| 110 | 1998-10-27 | Siding started, finish lumber delivered
| 108 | 1998-10-29 | Counter top installer reviewed job and provided price
| 103 | 1998-11-03 | Ordered laminate counter tops
| 98 | 1998-11-08 | Hardwood floors delivered to house
| 97 | 1998-11-09 | Installed hardwood floors
| 95 | 1998-11-11 | Counter tops installed, Water heater installed
3 | 90 | 1998-11-16 | Stair parts arrived
| 88 | 1998-11-18 | Called for mirror quote
| 86 | 1998-11-20 | Received prices for mirrors
| 85 | 1998-11-21 | Counted number of door handles to buy for finish carpenter to install
| 84 | 1998-11-22 | Railing started
| 78 | 1998-11-28 | Finish carpenter finished stairs
| 71 | 1998-12-05 | Drywallers repaired walls, cleaned house
| 69 | 1998-12-07 | Called escavator to touch up grade
| 65 | 1998-12-11 | Painter started painting
2 | 57 | 1998-12-19 | Painters finished, bought cable & phone wall covers
| 56 | 1998-12-20 | Installed wall covers, cleaned house
| 55 | 1998-12-21 | Called final installs for heating, plumbing, electrical and alarm
| 47 | 1998-12-29 | Plumbing finished, called inspection
| 46 | 1998-12-30 | Plumbing inspection failed - list on Window to correct, electrician started
| 45 | 1998-12-31 | Cleaned house
| 41 | 1999-01-04 | Called re-inspection for plumber, electrician started final, called for mirror install
| 39 | 1999-01-06 | Bought light bulbs
| 37 | 1999-01-08 | Mirrors installed
| 35 | 1999-01-10 | Cleaned house, touched up paint
1 | 30 | 1999-01-15 | Plumbing inspection final passed
| 28 | 1999-01-17 | Final Electrical inspector couldn't get into house - need to reschedule
| 27 | 1999-01-18 | Electical failed - need to get items fixed and re-schedule
| 20 | 1999-01-25 | Electrical passed
| 14 | 1999-01-31 | Cleaned house
| 13 | 1999-02-01 | Called for carpet measure
| 8 | 1999-02-06 | Called final inspection
| 6 | 1999-02-08 | Failed final inspection
| 4 | 1999-02-10 | Had inspector meet me at the house to agree on fixes
| 3 | 1999-02-11 | Corrected issues and recalled inspection
| 1 | 1999-02-13 | Final approved
| 0 | 1999-02-14 | Carpets installed.